## Bulan 2
No | HARI | TANGGAL | KEGIATAN | KELUARAN | STATUS
1 | Rabu | 9/20/2023 | Kemajuan APP | Penambahan fitur sycn data | done
2 | Kamis | 9/21/2023 | Kemajuan APP | Preparation Deploy aplikasi di sever & unit test | done
3 | Jumat | 9/22/2023 | Kemajuan APP | Proses Deployment | done
4 | Sabtu | 9/23/2023
5 | Minggu | 9/24/2023
6 | Senin | 9/25/2023 | Kemajuan APP | Penambahan fitur progress total | done
7 | Selasa | 9/26/2023 | Kemajuan APP | Penambahan Fitur Komentar bergambar | done
8 | Rabu | 9/27/2023 | Kemajuan APP | Pembuatan CDN image Uploader | done
9 | Kamis | 9/28/2023 | Kemajuan APP | Integrasi Sistem CDN | done
10 | Jumat | 9/29/2023 | Kemajuan APP | Optimasi User Experience | done
11 | Sabtu | 9/30/2023
12 | Minggu | 2023-01-10
13 | Senin | 2023-02-10 | I-PIT | Pembuatan Arsitektur | done
14 | Selasa | 2023-03-10 | I-PIT | Building Framework UI scratch Dashboard Admin | done
15 | Rabu | 2023-04-10 | I-PIT | Build MapBox & setup layer | done
16 | Kamis | 2023-05-10 | I-PIT | Create tile38 komputasi geofencing | done
17 | Jumat | 2023-06-10 | I-PIT | Integration Socket io realtime broadcast on room | done
18 | Sabtu | 2023-07-10
19 | Minggu | 2023-08-10
20 | Senin | 2023-09-10 | I-PIT | Add feature editing boundries | done
21 | Selasa | 2023-10-10 | I-PIT | Building Backend CRUD to DB | done
22 | Rabu | 2023-11-10 | I-PIT | Building Geofencing Logic | done
23 | Kamis | 2023-12-10 | I-PIT | Integrasi Backend ke dashboard | done
24 | Jumat | 10/13/2023 | I-PIT | AUTHENTIFIKASI | done
25 | Sabtu | 10/14/2023
26 | Minggu | 10/15/2023
27 | Senin | 10/16/2023 | Kemajuan APP & I-PIT | Rapat Terpusat Bersama Manager IT | done
28 | Selasa | 10/17/2023 | I-PIT | Pembuatan Menu administrator | done
29 | Rabu | 10/18/2023 | I-PIT | Rapat Bersama Client unit UluBelu | done
| Mengetahui |  |  | Tertanda
| Rudi Nurhidayanto |  |  | Fandilla Dimas Prayoga

## Bulan 3
No | HARI | TANGGAL | KEGIATAN | KELUARAN | STATUS
1 | Kamis | 2023-10-19 | Kemajuan APP | Redesign arsitekture aplikasi kemajuan | done
2 | Jumat | 2023-10-20 | Kemajuan APP | Pembuatan schema baru database | done
3 | Sabtu | 2023-10-21
4 | Minggu | 2023-10-22
5 | Senin | 2023-10-23 | Kemajuan APP | Pembuatan fitur Teams | done
6 | Selasa | 2023-10-24 | Kemajuan APP | Pembuatan UI list project team | done
7 | Rabu | 2023-10-25 | Kemajuan APP | Pembaruan fitur Add task | done
8 | Kamis | 2023-10-26 | Kemajuan APP | Pembaruan fitur Edit task | done
9 | Jumat | 2023-10-27 | Kemajuan APP | Pembuatan Backend Web Socket | done
10 | Sabtu | 2023-10-28
11 | Minggu | 2023-10-29
12 | Senin | 2023-10-30 | Kemajuan APP | Pembuatan file Exporter module | done
13 | Selasa | 2023-10-31 | Kemajuan APP | implementasi new schema ke backend Golang | done
14 | Rabu | 2023-11-01 | Kemajuan APP | Integrasi sistem terbaru web socket dengan UI | done
15 | Kamis | 2023-11-02 | Kemajuan APP | Bugs fixing fitur komentar | done
16 | Jumat | 2023-11-03 | Kemajuan APP | Penambahan fitur edit delete pada komentar | done
17 | Sabtu | 2023-11-04
18 | Minggu | 2023-11-05
19 | Senin | 2023-11-06 | Kemajuan APP | Penambahan fitur start project pada task | done
20 | Selasa | 2023-11-07 | Kemajuan APP | Bugs fixing layouting dan user experience | done
21 | Rabu | 2023-11-08 | Kemajuan APP | Penambahan fitur asignment task troops | done
22 | Kamis | 2023-11-09 | Kemajuan APP | Restruktur Backend CRUD Project | done
23 | Jumat | 2023-11-10 | Kemajuan APP | Integrasi dengan backend terbaru | done
24 | Sabtu | 2023-11-11
25 | Minggu | 2023-11-12
26 | Senin | 2023-11-13 | Kemajuan APP | Bugs fixing kalkulasi persentase progress | done
27 | Selasa | 2023-11-14 | Kemajuan APP | Pembuatan filtering data berdasarkan status | done
28 | Rabu | 2023-11-15 | Kemajuan APP | Pembuatan pagination tab di list project | done
29 | Kamis | 2023-11-16 | Kemajuan APP | Beta Fitur Kemajuan Board Kolaborator | done
30 | Jumat | 2023-11-17 | Kemajuan APP | Doployment on Production Server | done
| Mengetahui |  |  | Tertanda
| Rudi Nurhidayanto |  |  | Fandilla Dimas Prayoga

## Bulan 3 (2)
No | HARI | TANGGAL | KEGIATAN | KELUARAN | STATUS
1 | Kamis | 2023-10-19 | Kemajuan APP | Redesign arsitekture aplikasi kemajuan | done
2 | Jumat | 2023-10-20 | Kemajuan APP | Pembuatan schema baru database | done
3 | Sabtu | 2023-10-21
4 | Minggu | 2023-10-22
5 | Senin | 2023-10-23 | Kemajuan APP | Pembuatan fitur Teams | done
6 | Selasa | 2023-10-24 | Kemajuan APP | Pembuatan UI list project team | done
7 | Rabu | 2023-10-25 | Kemajuan APP | Pembaruan fitur Add task | done
8 | Kamis | 2023-10-26 | Kemajuan APP | Pembaruan fitur Edit task | done
9 | Jumat | 2023-10-27 | Kemajuan APP | Pembuatan Backend Web Socket | done
10 | Sabtu | 2023-10-28
11 | Minggu | 2023-10-29
12 | Senin | 2023-10-30 | Kemajuan APP | Pembuatan file Exporter module | done
13 | Selasa | 2023-10-31 | Kemajuan APP | implementasi new schema ke backend Golang | done
14 | Rabu | 2023-11-01 | Kemajuan APP | Integrasi sistem terbaru web socket dengan UI | done
15 | Kamis | 2023-11-02 | Kemajuan APP | Bugs fixing fitur komentar | done
16 | Jumat | 2023-11-03 | Kemajuan APP | Penambahan fitur edit delete pada komentar | done
17 | Sabtu | 2023-11-04
18 | Minggu | 2023-11-05
19 | Senin | 2023-11-06 | Kemajuan APP | Penambahan fitur start project pada task | done
20 | Selasa | 2023-11-07 | Kemajuan APP | Bugs fixing layouting dan user experience | done
21 | Rabu | 2023-11-08 | Kemajuan APP | Penambahan fitur asignment task troops | done
22 | Kamis | 2023-11-09 | Kemajuan APP | Restruktur Backend CRUD Project | done
23 | Jumat | 2023-11-10 | Kemajuan APP | Integrasi dengan backend terbaru | done
24 | Sabtu | 2023-11-11
25 | Minggu | 2023-11-12
26 | Senin | 2023-11-13 | Kemajuan APP | Bugs fixing kalkulasi persentase progress | done
27 | Selasa | 2023-11-14 | Kemajuan APP | Pembuatan filtering data berdasarkan status | done
28 | Rabu | 2023-11-15 | Kemajuan APP | Pembuatan pagination tab di list project | done
29 | Kamis | 2023-11-16 | Kemajuan APP | Beta Fitur Kemajuan Board Kolaborator | done
30 | Jumat | 2023-11-17 | Kemajuan APP | Doployment on Production Server | done
| Mengetahui |  |  | Tertanda
| Rudi Nurhidayanto |  |  | Fandilla Dimas Prayoga